## Live Projects
Alt Crossens Action Plan
Project Name & Brief Description | Key Drivers | 1. Developing an evidence base | 2. Delivering Integrated Water Management | 3. Opportunities for using the water environment | 4. Engaging the community | 5. Delivering cleaner and healthier waterbodies | 6. Enhancing the natural aspects of our catchment | Lead (name & org.) | Additional partners (name and org.) | Cost (£) | Target funding streams | Delivery date | Updates | RAG
Water Friendly Farming Appointment of a farming advisor to engage with farmers through workshops and encourage and implement better farm practice | Water quality, channel morphology, public engagement |  | ü |  |  | ü | ü | Paul Corner, Mersey Rivers Trust | Helen Dix, Environment Agency Michael Graham, Natural England Adam Briggs, NFU | 35000 | WEIF (Environment Agency) Other match needed | 2020-03-31 | Jan 2019: Project mandate submitted to Environment Agency for 2019-20 programme (£25k). £8k of match funding required if successful. Feb 2019: Likely to be successful in securing WEIF funding for phase 2 if the expected amount of funding is realised. | R - not started
Urban Alt misconnections & River Restoration Phase 1 (2018/19) Scoping and design of wetlands to improve water quality and morphology in the urban Upper Alt Catchment Phase 2 (2019/20) Delivery of priority wetland(s) as designed in phase 1 | Water quality, channel morphology, public engagement | ü | ü |  | ü | ü | ü | Rebecca Howard, Mersey Rivers Trust | Helen Dix, Environment Agency | Phase 1: £33,000 Phase 2: £70,000 | WEIF (Environment Agency) Other match needed | Phase 1: 31 March 2019 Phase 2: 31 March 2020 | Jan 2019: Funding for phase 1 secured and contractors evaluated. Awaiting confirmation of legal agreement to appoint contractors. Project mandate submitted for phase 2 funding from WEIF in 2019-20 (£50k). £20k of match funding required if successful. Feb 2019: Project formally agreed. Water quality contractors completed sampling. Design contractors to be appointed. Likely to be successful in securing WEIF funding for phase 2 if the expected amount of funding is realised. | A - in progress
The Pool De-culverting project Deculvert a section of culverted water course in Churchtown for flood risk and ecological benefits | Flood risk, channel morphology, public engagement |  | ü |  | ü |  | ü | Paul Corner, Mersey Rivers Trust | XXX Sefton Council Helen Dix, Environment Agency | 44000 | WEIF (Environment Agency) Local Levy (Sefton Council) | 2020-03-31 | Jan 2019: Project mandate submitted to Environment Agency for 2019-20 programme (£20k). £20k of match funding required if successful. | R - not started
The Pool (Southport) | Flood Risk to 52 properties | [6 empty] | Sefton Council | Mersey Rivers Trust / Environment Agency | £90k | FDGiA | 2019/2020 |  | A - in progress
Motorway Run-off Surveying water quality & quantity of all river and stream crossing points along the motorway network in Alt/Crossens, Lower Mersey & Douglas Catchments. | Water quality, flood risk, habitat | ü | ü |  |  | ü | ü | Paul Corner, Mersey Rivers Trust Sara Clowes, Groundwork | Highways England LAs Andrea Robson & Helen Dix, Environment Agency Mike Norbury, Mersey Forest | Feasability £200,000 Delivery £2.5m | Highways England Environmental designated Fund |  |  | Developing
Alt Catchment Study Academic study of CIP2 C2C data, to inform and prioritise water quality actions | Water Quality - Prority substances which may be extended to include Phosphorous |  |  |  |  | ü |  | Louisa Simpson-Brown, United Utilities | All partners to be included |  | Water Company funded | 2021-12-31 | Scope of works being developed -envisage a thirs year undergraduate project commencing Sept 20 | Developing

## Completed Projects
Alt Crossens Action Plan
Project Name & Brief Description | Key Drivers | 1. Developing an evidence base | 2. Delivering Integrated Water Management | 3. Opportunities for using the water environment | 4. Engaging the community | 5. Delivering cleaner and healthier waterbodies | 6. Enhancing the natural aspects of our catchment | Lead (name & org.) | Additional partners (name and org.) | Cost (£) | Funding streams | Delivery date | Updates | RAG
Call of Nature Septic tank enagement project raising awareness of issues to watercourses. River Guardians. | Water quality, public engagement, volunteers | ü |  |  | ü | ü |  | Rebecca Howard, Mersey Rivers Trust | Helen Dix, Environment Agency |  | EA | 2017-03-31 |  | Completed
Martin Mere Diffuse Pollution Improving water quality in the main river by using the restored ditch as an on-line SuDS system, filtering the run-off from the lakes which were shown to have high ammonia and phosphate levels. River Guardians. | Water quality, habitat, volunteers | ü | ü |  | ü | ü |  | Paul Corner, Mersey Rivers Trust | Helen Dix, Environment Agency | 41000 | EA Catchment Partnership Action Fund (CPAF) | 2016-05-01 |  | Completed